## Sheet1
PIP Sprint
Overall Task | Sub-Task | Deadline | Real Finishing Date | Status | On-Schedule
User Input Collection | Create form | 2021-09-03 | 2021-09-03 | Finished | Early
| Add Input Box | 2021-09-03 | 2021-09-03 | Finished | Early
| Submit Button | 2021-09-03 | 2021-09-03 | Finished | Early
| Receive User Input | 2021-09-03 | 2021-09-03 | Finished | Early
| Escape User Input | 2021-09-03 | 2021-09-03 | Finished | Early
| Process User Input | 2021-09-03 | 2021-09-03 | Finished | Early
University Administration System | Add Student's details | 2021-09-10 | 2021-09-03 | Finished | On Time
| Add University's details | 2021-09-10 | 2021-09-04 | Finished | On Time
| Create EER Diagram | 2021-09-09 | 2021-09-07 | Finished | Early
| Admissions Process | 2021-09-10 |  | In Progress
| Search Operations | 2021-09-10 |  | In Progress
| Count Operations | 2021-09-10 |  | In Progress
| Update Operations | 2021-09-10 | 2021-09-03 | Finished | Early
| Delete Operations | 2021-09-10 | 2021-09-03 | Finished | Early
| Fill Exam Form | 2021-09-17 |  | In Progress
| Appear fro Exam | 2021-09-17 |  | In Progress
| File Handling | 2021-09-17 |  | In Progress
| DataBase Operations | 2021-09-17 | 2021-09-10 | Finished
| Deployment | 2021-09-17 |  | Pending
Docker Image and Hub | Package App | 2021-09-24 |  | Pending
| Join Network | 2021-09-24 |  | Pending
| Connect to DataStore | 2021-09-24 |  | Pending
| Services for Pods | 2021-09-24 |  | Pending
| Increase Replicas | 2021-09-24 |  | Pending