## Sheet1
PIP Sprint
Overall Task | Sub-Task | Deadline | Real Finishing Date | Status
User Input Collection | Create form | 2021-09-03 | 2021-09-03 | Finished
| Add Input Box | 2021-09-03 | 2021-09-03 | Finished
| Submit Button | 2021-09-03 | 2021-09-03 | Finished
| Receive User Input | 2021-09-03 | 2021-09-03 | Finished
| Escape User Input | 2021-09-03 | 2021-09-03 | Finished
| Process User Input | 2021-09-03 | 2021-09-03 | Finished
University Administration System | Add Student's details | 2021-09-10 | 2021-09-03 | Finished
| Add University's details | 2021-09-10 | 2021-09-06 | Finished
| Admissions Process | 2021-09-10
| Search Operations | 2021-09-10
| Count Operations | 2021-09-10
| Update Operations | 2021-09-10
| Delete Operations | 2021-09-10
| Fill Exam Form | 2021-09-17
| Appear fro Exam | 2021-09-17
| File Handling | 2021-09-17
| DataBase Operations | 2021-09-17
| Deployment | 2021-09-17
Docker Image and Hub | Package App | 2021-09-24
| Join Network | 2021-09-24
| Connect to DataStore | 2021-09-24
| Services for Pods | 2021-09-24
| Increase Replicas | 2021-09-24